## WSS0137 Doors
Door Number | Door Name | Building Section | Head End | Cable Ran | CR | DC | REX | Lock | ADO | Tested | Notes
1 | 101A |  | 117 | Done | Done | Done, not working | N/A | Done | Temp working | All except ADO and DPS retest | ADO was temporarily wired for operation when the doors were scheduled unlocked for the purse of occupancy permit. Need to adjust wiring and complete and test programming.
2 | 101B |  | 117 | Done | Done | Done, not working | N/A | Done | Temp working | All except ADO and DPS retest | ADO was temporarily wired for operation when the doors were scheduled unlocked for the purse of occupancy permit. Need to adjust wiring and complete and test programming.
3A | 343A |  | 341 | Done | N/A | Done | N/A | Done | Temp working | All except ADO | ADO was temporarily wired for operation when the doors were scheduled unlocked for the purse of occupancy permit. Need to adjust wiring and complete and test programming.
3B | 343B |  | 341 | Done | N/A | Done | N/A | Done | N/A | Done
3C | 343C |  | 341 | Done | Done | Done, not working | N/A | Done | Temp working | All except ADO | Bad solenoid on one side. ADO was temporarily wired for operation when the doors were scheduled unlocked for the purse of occupancy permit. Need to adjust wiring and complete and test programming.
4D | 343D |  | 341 | Done | Done | Done | N/A | Done | Temp working | All except ADO | ADO was temporarily wired for operation when the doors were scheduled unlocked for the purse of occupancy permit
4E | 343E |  | 341 | Done | N/A | Done | N/A | Done | N/A | Done
4F | 343F |  | 341 | Done | N/A | Done | N/A | Done | Temp working | All except ADO | Bad solenoid on one side. ADO was temporarily wired for operation when the doors were scheduled unlocked for the purse of occupancy permit. Need to adjust wiring and complete and test programming.
5 | 510A |  | 341 | Done | Done | Done | N/A | Done | Not Done | Done | Pending ADO addition
6B | 408B |  | 512 | Done | Done | Not Done | N/A | Not Done | N/A | Not Done | wrong hinges
6C | 408C |  | 512 | Done | N/A | Not Done | N/A | Not Done | N/A | Not Done | wrong hinges
7 | 335 |  | 314 | Done | Done | Done | N/A | Done | N/A | Done
8 | 304A |  | 314 | Done | Not Done | Done | N/A | Done | N/A | Not Done | Missing EL hardware
9 |  |  | 714 | Done | Not Done | Not Done | N/A | Not Done | N/A | Not Done | Still on old hardware
10 |  |  | 714 | Not Done | Not Done | Not Done | N/A | Not Done | Not Done | Not Done | Next Phase
11 |  |  | 714 | Not Done | Not Done | Not Done | N/A | Not Done | N/A | Not Done | Next Phase
12 |  |  | 714 | Not Done | Not Done | Not Done | N/A | Not Done | N/A | Not Done | Next Phase
13 | 126A |  | 117 | Done | Not Done | Not Done | N/A | Not Done | N/A | Not Done | Needs Conduit, Missing EL hardware
14 | 113B |  | 117 | Done | Done | Done | N/A | Done | N/A | Done, still need to check power to strike | Have to check if powersupply is hooked up for strike
EL1 | 306A |  | 117 | Not Done | Not Done | Not Done | N/A | Not Done | N/A | Not Done | Waiting on EC for path and new PS
EL2 |  |  | 714 | Not Done | N/A | Not Done | N/A | Not Done | Not Done | Not Done | Next Phase
M1 |  |  | 341 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M2 | 342B |  | 341 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M4 | 514A |  | 512 | Done | N/A | Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M5 | 518A |  | 512 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done
M6 | 519A |  | 512 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M7 | 519C |  | 512 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M8 | 519D |  | 512 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M9 | 407B |  | 512 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for conduit issue
M10 | 403C |  | 512 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M11 | 402C |  | 341 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M12 | 402B |  | 341 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M13 | 401 |  | 341 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M14 |  |  | 341 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M15 | 303A |  | 341 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M16 | 128A |  | 117 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path, cable pulled to wrong location
M17 |  |  | 714 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M18 |  |  | 714 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M19 |  |  | 714 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M20 |  |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Next Phase
M21 |  |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Next Phase
M22 |  |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Next Phase
M23 |  |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Next Phase
M24 |  |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Next Phase
M25 |  |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Next Phase
M26 |  |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Next Phase
M27 |  |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Next Phase
M28 |  |  | 714 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M29 |  |  | 714 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M30 | 128B |  | 117 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M31 |  |  | 117 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M32 | 514C |  | 512 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done
M33 | 126B |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | String pulled in frame
E-1 | Elevator |  | 512 | Done | Not Done | N/A | N/A | Not Done | N/A | Not Done
E-2 | Elevator |  | 512 | Done | Not Done | N/A | N/A | Not Done | N/A | Not Done
E-3 | Elevator |  | 117 | Done | Not Done | N/A | N/A | Not Done | N/A | Not Done
E-4 | Elevator |  | 177 | Not Done | Not Done | N/A | N/A | Not Done | N/A | Not Done | Waiting on EC path
M34 |  |  | 512 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Pool Add, waiting on EC
M35 |  |  | 314 | Done | N/A | Done | N/A | N/A | N/A | Not Done | Main Gym Add