## WSS0137 Doors
Door Number | Door Name | Building Section | Head End | Cable Ran | CR | DC | REX | Lock | ADO | Tested | Notes
1 | 101A |  | 117 | Done | Not Done | Done | N/A | Done | Not Done | Not Done
2 | 101B |  | 117 | Done | Not Done | Done | N/A | Done | Not Done | Not Done
3A | 343A |  | 341 | Done | N/A | Not Done | N/A | Done | N/A | Not Done | Missing EL hardware
3B | 343B |  | 341 | Done | N/A | Not Done | N/A | Done | N/A | Not Done | Missing EL hardware
3C | 343C |  | 341 | Done | Not Done | Not Done | N/A | Done | Not Done | Not Done
4D | 343D |  | 341 | Done | Not Done | Not Done | N/A | Not Done | Not Done | Not Done | Missing EL hardware
4E | 343E |  | 341 | Done | Not Done | Not Done | N/A | Not Done | N/A | Not Done | Missing EL hardware
4F | 343F |  | 341 | Done | N/A | Not Done | N/A | Not Done | N/A | Not Done | Missing EL hardware, Added ADO?
5 | 510A |  | 341 | Done | Not Done | Done | N/A | Not Done | Not Done | Not Done | Missing EL hardware
6B | 408B |  | 512 | Not Done | Not Done | Not Done | N/A | Not Done | N/A | Not Done | Missing EL hardware, wrong hinges
6C | 408C |  | 512 | Not Done | N/A | Not Done | N/A | Not Done | N/A | Not Done | Missing EL hardware, wrong hinges
7 | 335 |  | 314 | Not Done | Not Done | Not Done | N/A | Not Done | N/A | Not Done
8 | 304A |  | 314 | Done | Not Done | Done | N/A | Done | N/A | Not Done | Missing EL hardware
9 |  |  | 714 | Done | Not Done | Not Done | N/A | Not Done | N/A | Not Done | Still on old hardware
10 |  |  | 714 | Not Done | Not Done | Not Done | N/A | Not Done | Not Done | Not Done | Next Phase
11 |  |  | 714 | Not Done | Not Done | Not Done | N/A | Not Done | N/A | Not Done | Next Phase
12 |  |  | 714 | Not Done | Not Done | Not Done | N/A | Not Done | N/A | Not Done | Next Phase
13 | 126A |  | 117 | Done | Not Done | Not Done | N/A | Not Done | N/A | Not Done | Needs Conduit, Missing EL hardware
14 | 113B |  | 117 | Done | Not Done | Done | N/A | Not Done | N/A | Not Done | Missing EL hardware
EL1 | 306A |  | 117 | Not Done | Not Done | Not Done | N/A | Not Done | N/A | Not Done | Waiting on EC for path and new PS
EL2 |  |  | 714 | Not Done | N/A | Not Done | N/A | Not Done | Not Done | Not Done | Next Phase
M1 |  |  | 341 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M2 | 342B |  | 341 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M4 | 514A |  | 512 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M5 | 518A |  | 512 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | String to frame
M6 | 519A |  | 512 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | String to frame
M7 | 519C |  | 512 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | String to frame
M8 | 519D |  | 512 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | String to frame
M9 | 407B |  | 512 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for conduit issue
M10 | 403C |  | 512 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M11 | 402C |  | 341 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M12 | 402B |  | 341 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M13 | 401 |  | 341 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M14 |  |  | 341 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M15 | 303A |  | 341 | Done | N/A | Done | N/A | N/A | N/A | Not Done
M16 | 128A |  | 117 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M17 |  |  | 714 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M18 |  |  | 714 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M19 |  |  | 714 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M20 |  |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Next Phase
M21 |  |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Next Phase
M22 |  |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Next Phase
M23 |  |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Next Phase
M24 |  |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Next Phase
M25 |  |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Next Phase
M26 |  |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Next Phase
M27 |  |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Next Phase
M28 |  |  | 714 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M29 |  |  | 714 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M30 | 128B |  | 117 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M31 |  |  | 117 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for path
M32 | 514C |  | 512 | Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Waiting on EC for conduit
M33 | 126B |  | 714 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | String pulled in frame
E-1 | Elevator |  | 512 | Not Done | Not Done | N/A | N/A | Not Done | N/A | Not Done
E-2 | Elevator |  | 512 | Not Done | Not Done | N/A | N/A | Not Done | N/A | Not Done
E-3 | Elevator |  | 117 | Not Done | Not Done | N/A | N/A | Not Done | N/A | Not Done
E-4 | Elevator |  | 177 | Not Done | Not Done | N/A | N/A | Not Done | N/A | Not Done | Waiting on EC path
M34 |  |  | 512 | Not Done | N/A | Not Done | N/A | N/A | N/A | Not Done | Pool Add, waiting on EC
M35 |  |  | 314 | Done | N/A | Done | N/A | N/A | N/A | Not Done | Main Gym Add